## RESCUE PHASE 1
PHASE 1: FINANCIAL RESCUE
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR 1: GOVERNANCE
1 | Governance, Council and oversight structures/Committees | The municipality has an elected Speaker, Acting Executive Mayor and Acting Chief Whip. | Permanent Executive Mayor and Chief Whip to be electing before the end of June 2023 as a court order has been made. | In house | In house, CoGTA NT PT | CM | 01/08/2023 | 30.08.2023 | Improved governance and accountability. Statutory reports submitted timeously. Roles clarified. | Council resolution on the elections | Financial benefits to be achieved through improved operational efficiencies
|  | All section 79 and 80 oversight structures are in place and now functional, after a period of instability experienced by the municipality. Chairperson of MPAC not in place. Terms of reference for the Programming Committee not developed yet. | MPAC chairperson to be elected/appointed by end of June 2023. Terms of reference to be finalised by end of June 2023. | In house | Inhouse | Director: Corporate Services | 01.08.2023 | 31/12/2023 |  | Council resolution. Approved Terms of reference.
|  | The municipality has a manual resolutions register but not being effectively monitored for implementation. | Council resolutions implementation to form part of Executive management for effective monitoring and the status be tabled at Council regularly. | In house | In house | Speaker | 01/08/2023 | Quarterly |  | EMC minutes
|  | The municipality has one public entity. The SLA with CENTLEC does not provide for revenue to be transferred to the municipality. | Council should review the SLA to ensure that the municipality receives revenue as per reviewed SLA. | In house | In house COGTA | Office of the Speaker & CM | 01.08.2023 | 30.08.2023 |  | Reviewed SLA
|  | Disciplinary Board not in place and therefore not functional. | Re-advert to be placed urgently for the appointment of the new Disciplinary Board. | In house | In house | CFO | 01/08/2023 | Monthly | Financial misconduct recorded. | Copy of the advert
|  | Councillors and staff declare their interests in registers but there is no monitoring process of the status of the declarations. | Develop a process plan of monitoring declaration of interests by councillors and staff. | In house | In house | Office of the Speaker & CM | 01/08/2023 | Quarterly | Quarterly reports | Process plan for monitoring declarations. Council resolutions of approved reports.
|  | Council does not approve statutory reports timeously in line with the approved MFMA calendar, e.g MPAC report, Annual Report for 2022/23 not yet tabled, budget not yet passed, etc. | New leadership and City Manager to ensure urgent approval of all reports in line with the MFMA calendar.
2 | Political Interference | It is alleged that politicians interfere in the administration and specifically in staff appointments and procurement. There are tensions between Council and senior Management and mutual mistrust exist, whether permanent, acting or deployed officials. | The Accounting Officer must act on political interference, that includes instituting criminal charges against Councillors that interfere in the administration of the Municipality. Enforcement of the Code of Conduct for councillors These should also be escalated to the National and Provincial and respective State Institutions. | In house | In house, CoGTA NT PT | CM | 01/08/2023 | 31/12/2023 | Improved governance and accountability. | Opened criminal cases Escalation report | Financial benefits to be achieved through improved operational efficiencies
3 | System of Delegations | The system of delegations is outdated and in certain areas not in line with local government recent legislative amendments. | Develop process plan for the development of a system of delegations with clear deliverables and timeframes and identify responsible officials , develop delegations register. | In house | In house | CM & CFO | 01/08/2023 | 31/12/2023 | Systems of delegations in place | Process plan, Approved Delegations of authority and delegations register. | Financial benefits to be achieved through improved operational efficiencies
|  | There are no updated delegation registers in place; | Sub-delegate powers and functions to Heads of directorate. | In house | In house |  | 01/08/2023 | 31/12/2023 | Enhanced accountability and, checks and balances. Sub-delegations in place Clarified roles | Signed sub-delegations and acknowledgement of receipt
|  | There are no written and signed sub-delegations below the City Manager. | Sub-delegate further to maximise administrative and operational efficiencies. | In house | In house |  | 01/08/2023 | 31/12/2023
|  | The old system of delegations does not incorporate role clarification as required by law and are centralised at the level of heads of departments | Incorporate Role clarification in the system of delegations as required by Systems Act. | In house | In house |  | 01/08/2023 | 31/12/2023 |  | Approved delegations that include role clarification.
|  |  | Conduct training on the system of delegations through CoGTA, National or Provincial Treasury. | In house | In house |  | 01/08/2023 | 31/12/2023 |  | Approved training programme, material, attendance register of councillors, training evaluation forms
|  | The City Manager did not delegate the powers and functions related to supply chain management and the establishment of Bid committees in line with statutory requirements. | Review and approve delegations of powers and functions for implementation of supply chain management policy including the establishment of Bid committees. | In house | In house |  | 01/08/2023 | 31/12/2023 |  | Approved SCM Delegations of authority.
4 | By-laws | Most by-laws are outdated and not recently reviewed. There are no financial By-laws promulgated for the current financial year 2023/24 | Develop a process plan for the review of by-laws and ensure implementation. | In house | In house | CM | 01/08/2023 | 31/12/2023 | Enforcement of law | Appproved By-laws
5 | UIF&W and Consequence Management | UIF&W is huge and increasing. The cumulate balances of UIF&W as at 30 June 2022 are as follows: Unauthorised: R 5.6 Billion. Irregular: R 3.1 Billion. Fruitless and Wasteful: R 240 Million. | Draft UIF&W report to be finalised for approval by Council. A reduction plan should be developed and implemented with clear timeframes. | In house | In house | CM and CFO | 01/08/2023 | 31/12/2023 | Reduction in historic UIFW expenditure Implementation of consequence management (disciplinary processes, recovery of money, reported criminal cases) | Approved UIF&W report Approved Reduction Plan | Financial benefits to be achieved through improved operational efficiencies
|  | There are no section 32 investigations that have been conducted. The analysis and identification of UIF&W was outsourced but the report is not being used by the municipality due to the irregular appointment of the service provider. | Conduct investigations on all reported allegations of financial misconduct against the officials and ensure consequence management is implemente once the Disciplinary Board has been established. Additional investigation should be conducted on the irregular appointment of the service provider. | In-house and NT-MF | In-house and NT-MFMA unit | CM CFO | 01/08/2023 | 31/12/2023 | Legislative compliance Consequence management | Approved UIF&W expenditure reduction plan . Written outcome of disciplinary hearings | Financial benefits to be achieved through improved operational efficiencies
|  | The MM is not submitting UIF&W expenditure reports quarterly to the Mayor and annually to the Council for oversight as required by Regulations. | Reporting on the UIF&W should be included in the municipality’s calendar for monitoring and implementation and quarterly to the Audit Committee. | In house | In house | CAE CFO | 01/08/2023 | Quarterly 30.09.2023 | Legislative compliance | Quarterly reports on UIF&W expenditure to Audit Commitee | Financial benefits to be achieved through improved operational efficiencies
6 | Service delivery | Protests over water and sewerage and poor service delivery happens regularly. The latest reported event was Municipal vehicles set alight as recent as March 2023. | Newly elected leadership should develop a service delivery recovery plan to deal with backlogs created by the political and administrative instability. | In house | In house | Office of the Speaker & CM | 01/08/2023 | 31/12/2023 | Improved service delivery | Service Delivery Recovery Plan | Financial benefits to be achieved through improved operational efficiencies
7 | Risk Management | The Municipality has a council approved Risk Management Policy that include the strategy and implementation plan. A new Risk Management Committee was appointed in March 2023 and was inducted in June 2023. The Municipality has a CRO in place. However, the Municipality does not have a Business Continuity Plan (BCP) in place. | The Municipality need to prioritise the development of the enterprise-wide BCP that will include the ICT BCP. | In house | In house | CM CRO Internal Audit | 01/08/2023 | 31/12/2023 | Monitored risks | Quarterly risk management reports approved by Administrator. Risk monitoring report. Monthly FRP implementation progress reports | Financial benefits to be achieved through improved operational efficiencies
Management should submit quarterly reports on implementation of mitigating measures against identified risks to risk management committee and Council.
Internal Audit to assist in monitoring risk mitigation measures in the Municipality.
8 | Contract Management | There is no functioning contract management system in place. Not clear where the function should be performed or located. There is no up-to-date contract register. | Revive the sitting of the Contract Management Committee. Consider re-locating this function to SCM. Establish an online document management system. Invite National Treasury and/or Provincial Treasury to conduct workshop on contract management. | In house | In house | CM and CFO | 01/08/2023 | 31/12/2023 | Contract Management Committee and Online Document Management System | Contract Management Committe ToRs and minutes. Approved Structural amendments. Online document management system. Workshop programme and attendance registers. | Financial benefits to be achieved through improved operational efficiencies
|  | The municipality has contracted services with service providers where there is staff employed to do the same work. Some contracts have not been signed by the previous MM. | Review existing contracts against the organisational structure to determine duplication of services. Investigate the validity of unsigned contracts. | In house | In house | CM & CFO | 01/08/2023 | 31/12/2023 | Improved contract management and accountability. | Review and investigation reports. | Financial benefits to be achieved through improved operational efficiencies
|  | The municipality has evergreen contracts that are automatically renewed without going back to the market. | Evergreen contracts to be investigated and reviewed for an open and tranparent procurement process to be undertaken. | In house | In house |  | 01/08/2023 | 31/12/2023 | Open and transparent procurement system | Investigation report, Advertised tender or RFP | Financial benefits to be achieved through improved operational efficiencies
9 | Litigation and Legal Landscape | The legal department is not functioning optimally and seemed to fail in its function to mitigate risk to the Municipality | A process plan must be developed and implemented where actions and legal threats against the Municipality is assessed to make the decision to defend or settle matters. Certain legal matters should be escalated to National Institutions (Hawks) for assistance | In-house, PT | In-house, PT | CM & CFO | 01/08/2023 | 31/12/2023 | Improved legal support. | Process plan and assessment report.Case numbers from the Hawks | Financial benefits to be achieved through improved operational efficiencies
|  | It seems that the legal department is not consulted as it should that leads to poor contracting, that includes procurement, and management, high litigation instances, policies not reviewed as required, little to no consequence management for employees implicated in irregular, unauthorised and fruitless expenditure and implementation of by-laws. | [6 empty] | Improved contract management and accountability. | Improved contract management and accountability | Financial benefits to be achieved through improved operational efficiencies
Contingent liabilities as at 30 June 2022 was R 83.9 million. Legal fees budgeted for 2021/22 was R 26.7 million with actual legal fees incurred at R 52.7 million.
Poor contract management has led to high number of litigations from service providers due to the flawed procurement process, non-payment of service providers, political instability and politicized administration that leads to litigations.
|  | The municipality has an updated litigation register but the tracking of court matters is not efficient. | Develop a litigation tracking system based on the litigation register. | In house | In house | Head: Corporate Support Services | 01.08.2023 | 31/12/2023 | Improved litigation management | Litigation tracking system
|  | The municipality has a legal support protocols in the form of standard operating procedures. However, there is no adequate capacity to provide adequate legal support. | Review legal Services organisational structure to ensure appropriate provision of posts for effective legal support. | In house | In house | Head: Corporate Support Services | 01.08.2023 | 31/12/2023 | Improved legal support. | Approved organisational structure amendments
|  | The municipality has a legitimate appointed panel of attorneys procured through an open tender process which ends in March 2023. However, they have taken the municipality to court due to non-payment caused by poor budgeting. | Budget for litigation/legal costs should be reviewed in line with municipality’s operational needs. Terms of reference for the new term of panel of attorneys should be developed for urgent advertising for procurement. | In house | In house | CM & CFO | 01/08/2023 | 31/12/2023 | Improved legal support. | Approved adjusted budget, ToRs for panel of attorneys.
10 | Information and Communication Technology | The ICT department has had instability and lack of leadership as there has been no Chief Technology Officer (CTO) since 2019 and no permanent managers since 2011. | Develop a recruitment plan for the urgent filling of ICT department posts. | In house | In house | CM & Head: Corporate Support Services | 01/08/2023 | 31/12/2023 | Improved ICT governane compliance | Approved appointments | Financial benefits to be achieved through improved operational efficiencies
|  | There is therefore no ICT strategy or centralisation and oversight of ICT. As a result, key systems are not in place such as document management system, contract management system and time and attendance. | Develop and implement an ICT Strategy, Centralise ICT function with a defined strategy and mandate to support the Municipality’s requirements and strategic imperatives. Develop and implement a clearly defined and resourced ICT Plan. | In house | In house | ICT Manager | 01/08/2023 | 31/12/2023 |  | Approved ICT Strategy and resourced ICT Plan
|  | Municipality does not have a list of licences and software currently in place and are paying for licences that are not being utilised as indicated by their excessive software license fees. | Review all licenses and their level of utilisation. Conduct training for maximum use of underutilised software. | In house | In house | ICT Manager | 01/08/2023 | 31/12/2023 | Improved records management | Review report, Training programme, attendance registers.
|  | The internal audit department does not have the resources and skills to carry out ICT audits. | Review internal audit capacity or outsource ICT audit function. | [6 empty] | Review report.
11 | Audit action plans (internal and external) | The Municipality received qualified audit outcomes for 2017/18 and 2018/19, improved to unqualified for 2019/20 and 2020/21 but regressed to qualified audit outcomes in the 2021/22. The past five financial years show stagnation in this regard. The Post Audit Action plan for the previous AG outcomes has not been tabled before Council for approval. The Action plan was discussed at the Mayoral Committee and EMT. | Management should develop and implement the post audit action plan timeously and report on progress in the Audit Steering Committee meetings. | In-house | In-house | CM | 01/08/2023 | Ongoing | Improved audit outcomes and/reduction of audit findings | Validated quarterly progress reports on the implementation of audit action plan and audit file | Financial benefits to be achieved through improved operational efficiencies
12 | Internal Audit | The Municipality’s Internal Audit function is in place and functional. However, recommendations of the Audit Committee have been partially implemented by the Municipality. The term of the current Audit Committee has ended on 31 May 2023 and Council is in the process of finalising the appointment of the new members. | Internal Audit should provide support and monitor the implementation of Audit Committee recommendations by management. | In-house | In-house | CM and CFO | 01/08/2023 | 31/12/2023 | Implementation of Audit Committee recommendations Appointing the new Audit Committee | Updated register of implementation of recommendations | Financial benefits to be achieved through improved operational efficiencies
The process of appointing the new Audit Committee should be fast-tracked.
PILLAR 2: INSTITUTIONAL
1 | Operating Model | MMM does not have a well-defined and approved organisational structure to support the functioning of the Municipality. The process for the review of the organisational structure has started however not yet concluded. | Finalise the review of the organisational structure in line with the Operating Model, current municipal budget & service delivery demands. | In-House | In house | CM & Head: Corporate Services | 01/08/2023 | 31/12/2023 | Viable Operating model | Approved reviewed Organisational structure | Financial benefits to be achieved through improved operational efficiencies
2 | Effective leadership and management | There is instability at MMM as the City Manager and Section 56 Appointments remain vacant or are filled with acting appointments. | Develop a Recruitment plan for the urgent filling CM and Section 56 Managers | In house | In house | CM & Head: Corporate Services | 01/08/2023 | 31/12/2023 | Improved leadership and operational management | Approved recruitment plan and appointments | Financial benefits to be achieved through improved operational efficiencies
3 | Employee Cost | Employee costs are currently 24.71% of the operating expenditure which is below the norm of 25%-40%. The low % could point to a high level of critical vacancies and general understaffing. | Conduct a Salaries benchmarking exercise to ensure employees are paid based according to the correct grading. | In-House | In house | D: CSS and CFO | 01/08/2023 | 31/12/2023 | Appropriately graded salaries | Benchmarking outcomes report | Achieve expenditure reduction financial targets per FRP parameters
4 | Management of overtime | Overtime is excessive | Conduct regular review and enforcement overtime policy in line with the Basic Conditions of Employment Act including adequate supervision. | In-House | In house | CM and D: CSS | 01/08/2023 | 31/12/2013 | Reduced Overtime costs | Overtime review report | Achieve expenditure reduction financial targets per FRP parameters
|  |  | Conduct quarterly monitoring of the implementation of the Overtime Policy by department. | In house | In house | D: CSS | 01/08/2023 | Quarterly |  | Quarterly overtime monitoring reports
|  |  | Perform an audit of the overtime per each department. | In house | In house | CAE | 01/08/2023 | 31/12/2023 |  | Overtime internal audit report
|  |  | Review the system description relating to overtime and identify control issues. | In house | In house | CIO | 01/08/2023 | 31/12/2023 |  | System review report
5 | Clarity about roles and responsibilities and performance management | There are defined roles and responsibilities but are not adhered to and no performance agreements and management thereof are in place. As a result, no consequence management can be implemented. | Review of roles and responsibilities against approved organogram. Implementation of performance management agreements. | In-House | In house | CM & Head: Corporate Services | 01/08/2023 | 31/12/2023 | Clear roles and responsibilities. Improved performance management | Approved Organisational Review Report, Signed Performance Agreements. | In line with the approved budget and the funding plan.
|  | No job descriptions and bloated salaries. | Conduct skills audit and define job descriptions. | [6 empty] | Skill Audit Report Job descriptins
6 | Filling of critical positions | There are delays in the filling of critical vacant posts with people that have the appropriate experience, skills and qualifications. | Organisational restructuring by assessing the critical posts required to operate efficiently and effectively and staff excess to requirements of the Municipality Develop a Recruitment plan. | In-House | In-house, CoGTA and NT-MFMA unit | CM & Head: Corporate Support Services | 01.08.2023 | 31/12/2023 | Capacitated municipality | Organisational restructuring report, Recruitment plan | Only use mobilised resources.
|  |  | Develop an HR strategy and Plan that guides recruitment, placement of staff, retention of staff, performance management and disciplinary processes. |  |  |  | 01/08/2023 | 31/12/2023 |  | Approved HR Strategy and Plan
7 | Disciplinary Board | The disciplinary board is not functional, and there isn't an updated register. | Establishment of a functioning disciplinary board. | In-house | In-house | CM & Head: Corporate Support Services | 01/08/2023 | 31/12/2023 | Functioning Disciplinary Board | Functioning Disciplinary Board | Financial benefits to be achieved through improved operational efficiencies
|  |  | Develop and regularly update the disciplinary case management register. | [5 empty] | Approved disciplinary case management register | Approved disciplinary case management register
8 | Performance management | Performance Management System not in place. No performance agreements for senior managers in place Performance assessment not conducted. | Develop a functioning performance management system. | In-house | In-house | CM & Head: Corporate Support Services | 01/08/2023 | 31/12/2023 | Functioning performance management system | Functioning performance management system | Financial benefits to be achieved through improved operational efficiencies
|  |  | Develop process plan and policy to Cascade Performance to levels below Senior Managers. | [5 empty] | Performance Management Process Plan | Performance Management Process Plan
|  |  | Implement consequence management for non-performance. | [5 empty] | Written outcome of disciplinary hearings | Written outcome of disciplinary hearings
9 | Consequence Management | Lack of accountability and consequence management in the municipality impacts service delivery and municipal finance management. | Develop and implement of Consequence Management Policy. | In-house | In-house | Director Corporate Services | 01/08/2023 | 31/12/2023 | Approved Consequence management policy | Financial assessment reports | Financial benefits to be achieved through improved operational efficiencies
|  |  | Conduct Workshops to communicate the Code of Conduct for staff and Councillors. | [6 empty] | Attendance register for workshop
|  |  | Develop process to report and monitor cases . | [6 empty] | Approved Consequence management SOPs
10 | Physical Verification of staff and qualifications | Existence of employees unaccounted for (‘ghost workers’). | Conduct an employee head count and identify any ghost employees or employee’s surplus to the organisation, on the payroll. | In-house | In-house | Director Corporate Services | 01/08/2023 | 31/12/2023 | Completeness of employee related costs | Employee Verification Report | Reduction in employee cost
|  |  | Implement an attendance register be it electronic or manual. | [6 empty] | Daily attendacne register
11 | Records Management | Poor record keeping due to decentralisation of records management and limited capacity. Missing documents. No records disposal being undertaken. Loss of municipality records. | Develop a file plan in accordance with the National and Provincial Archives Services guidelines. | In-house | In-house | Director Corporate Services | 01/08/2023 | 31/12/2023 | Improved records management. Improved audit outcomes. | Approved File Plan | Financial benefits to be achieved through improved operational efficiencies
Provide Training for all staff on importance of document management and POPIA act.
Develop a Records Centralisation process plan for implementation.
Implement a records system that is compliant with National Archives and National Treasury.
12 | Policy Management | Policies are outdated and last reviewed during 2017 and there is no clarity on who is responsible for drafting and reviewing policies. | Develop a process plan to review outdated policies and develop policies not in place. | In-House | In house | CM & Head: Corporate Support Services | 01.08.2023 | 31/12/2023 | Improved policy management. Legislative compliance | Policy review and development process plan. Approved policies | Financial benefits to be achieved through improved operational efficiencies
13 | Change Management | Change Management is not implemented. | Sensitise employees and organised labour about the current financial state and the introduction of the FRP. | In-house | Director Corporate Services NT-MFRS | Director Corporate Services | 01/08/2023 | 31/12/2023 | Achieved buy-in and support/ Set tone for change. Staff morale boosted. Enhanced service delivery & performance. Increased productivity to support Revenue Management operations. | Attendance Register | Financial benefits to be achieved through improved operational efficiencies
|  |  | Undertake a diagnostic process (climate survey) to determine the level of staff morale and satisfaction. | [6 empty] | Completed Employee satisfaction Survey Questions and Report
|  |  | Develop a change management strategy . | [6 empty] | Change Manegement Strategy Council resolution
PILLAR THREE: FINANCIAL MANAGEMENT
1 | ESKOM | Escalating ESKOM debt. | Consider application for MFMA Circular No. 124 – Municipal Debt Relief through National Treasury. | In-house | In-house | CM and CFO | Immidiate | 12 Months | Maintaining the Eskom bulk current account A funded MTREF Cost reflective tariffs Electricity and water as collection tools 80% average quarterly collection of property rates and service charges Municipality’s billing system perfectly aligns to its Council approved GVR MFMA section 71 reporting Monthly reporting on progress in implementing its FRP to the Provincial Executive Provincial Treasury certification of Municipal compliance Limitation on Municipality borrowing powers Ensure proper management of resources | Monthly Provincial Treasury certification of Municipal compliance | Municipal Eskom Debt Relief as prescribed by Circular No. 124
|  |  | Adhere to the requirements and terms. |  |  |  | 01/07/2023 | Monthly
2 | Funded Budget and Budget Spending Limits | During the 2020/21 and 2021/22 financial years, MMM budgeted surpluses of R 1,035 billion (2020/21) and R 622,7 million (2021/22). The financial results for the two years reflected deficits of R 20,2 million (2020/21) and a deficit of R 872,7 million (2021/22) which clearly indicate that the budgets were not funded. Poor budgeting techniques and insufficient provision for the impairment of bad debt are the main contributors. In 2021/22 in respect of impairment of bad debts R933.4 million was budgeted and R1.8 billion had to be provided for. MMM had audited deficits for the past three financial years, and budget for surpluses for the MTREF period, which are not cash backed. The analysis of the operating surplus / (deficit) by service indicates that there is a disconnect between the budget and the historical audited results. MMM experienced significant losses since 2018/19 in the non-trading side of the business (General) and were unable to offset these losses against the barely profitable trading services. These losses have been significantly reduced in the MTREF period 2023 – 2025. With further analysis it was identified that the reason for the improvement in the budget is not with unrealistic increases in operating revenue (2022/23: 5%; 2023/24: 8%; and 2024/25: 6%) but rather a 15% reduction in operating expenditure for 2022/23 and 5% and 4% increases in 2023/24 and 2024/25 respectively. Whether this is achievable is questionable based on historical trends. | Prepare, approve, and implement a Budget Funding Plan for the MTREF period linked to the FRP strategies and financial targets (NT Support). Progress must be reported monthly and include targets as KPIs in performance plans. | In-house | NT Oversight | CFO (NT Oversight and Support) | 01/08/2023 | 31/12/2023 | 3-Year Budget Funding Plan Monthly BFP Progress Reports Credible 2023/24 MTREF Budget Plan for phasing in of cost-reflective tariffs | Approved 2023/24 MTREF Budget Approved Budget Funding Plan (BFP) BFP Progress Reports Cost-reflective tariff strategy | 100% adherence to approved 3-Year Budget Funding Plan FRP MTREF Financial Targets Target cash flow improvement per annum (in line with FRP targets)
Compile realistic cash backed budgets going forward.
Provide realistic allocations for the provision for debt impairment.
Ensure cost reflective tariffs and scrutinise expenditure for unnecessary expenditure.
Implement accurate budgeting for non-cash items to generate cash to move the municipality to a funded position.
Projected revenue should consider the low historical and future collection rates and use a probabilistic method of projecting for revenue.
Interest on debtors should only be charged on recoverable debts.
Track the expenses not in accordance with the budget and the votes for the past three years, establish a statistical relation with other elements of financials and revise the budget parameters for the expenses using the historical audited expenses, with inflation adjustment, as a base for forecasting.
Undertake a line item analysis of all budget line items to ensure that a realistic cash backed budget is approved.
3 | Funded Budget Status – Capital Budget | The capital budgets for 2020/21 and 2021/22 were only 80.6% and 46.23% spent respectively. This is because of poor cash flow and planning, as well as issues resulting from their poor supply chain management processes. As at 30 June 2022 cash on hand was R728.3 million with liabilities for payables and unspent conditional grants of R2.6 billion. There was an underspend of capital budget for each category of service lines except for Roads Infrastructure, which validates the point of poor cashflow and non-credible budgeting techniques. A high reliance was placed on grant funding to fund capital expenditure during the 2020/21 and 2021/2022 financial years. Compared to the budget MMM is relying on own sources (internally generated funds and loans) to fund planned capital expenditure. This is not realistic due to the current solvency and cash flow constraints. Capital expenditure should therefore be reprioritised within its spending capacity and cashflows. | Compile credible and cash backed capital budgets linked to the IDP’s capital project priorities and compiling and budgeting for a payment plan to pay the outstanding payables and unspent conditional grants. | In-house | CFO with NT Oversight | CFO (NT Oversight and Support) | 01/08/2023 | 31/12/2023 | 3-Year Budget Funding Plan Monthly BFP Progress Reports Credible 2023/24 MTREF Budget Plan for phasing in of cost-reflective tariffs | Approved 2023/24 MTREF Budget Approved Budget Funding Plan (BFP) BFP Progress Reports Cost-reflective tariff strategy | 100% adherence to approved 3-Year Budget Funding Plan FRP MTREF Financial Targets Target cash flow improvement per annum (in line with FRP targets)
Establish a plan on how new grant funding will be fully spent as part of their capital budget planning process, aligned to the IDP, else these funds are to be returned to National Treasury.
Training of SCM staff on SCM regulations.
Consequence management should be strengthened where SCM staff do not procure on time for invalid reasons.
Ensure unspent conditional grants are cash backed and are not being spent on operating expenditure.
Prescribe a minimum period for the filling of the acting positions so that strategies can be carried out. .
4 | Revenue Management | The total outstanding gross consumer receivables from exchange transactions was R 6,690,341,584 with the total allowance for impairment at R 5,309,741,295 as at 30 June 2022 which is 79% of outstanding debt. The annual collection rate for the three financial years under review were 83.12% (2019/20), 81.16% (2020/21) and 79.44% (2021/22). The norm is 95%. The inability to collect revenue and thereby convert revenue to cash is contributing the cash flow challenges being experienced by the Municipality. The calculated impact of the low collection ratio on cash flow for MMM indicate R914 million lost through poor collections in 2021/22 which equates to 66% of total revenue generated through property rates. Critical vacant posts are not filled. Broken meters not being fixed. Billing is inaccurate and not timeously sent out. The non-implementation of revenue enhancement measures. | Write off bad debts as per the approved credit control and debt collection policy. This will assist with determining the cash backed part of the accounts receivable. | In-house | CFO and NT Oversight | CFO | 01/08/2023 | 31/12/2023 | Increased own revenue Increased collection rate | Monthly reconciliations VR reconciliation S71 Reports | Per set revenue targets
Revenue enhancement initiatives need to be implemented and billing and collection and credit control processes need to be set and complied with.
Fill critical vacancies and ensure that the revenue value chain activities are streamlined.
Conducting quarterly VR reconciliation with the billing system. Metering (verification, auditing, and consistent reading of meters).
The previous cost of supply studies must be updated, and tariffs structures must be applied and implemented and for electricity NERSA’s approval.
Hand over the debtor’s book to debt collectors using a performance-based agreement that is traceable and measurable.
Contact government departments that owe the municipality and establish the payment terms. If that fails seek Provincial Treasury intervention.
Implement and update standard operating procedures for debtors’ management and training of internal staff.
Engage debtors to agree on payment arrangements.
5 | Cost-reflective Tariffs – Water and Electricity Services | The deficits for the 2020/21 and 2021/22 financial years show that cost reflective tariffs have not been set which indicates bad budgeting processes. The cost of sales of water exceeds the selling price, which is a direct result in losses. This is an indication that the tariffs charged are not cost reflective. Forecasted water and electricity tariffs are set without considering the growth rate in tariffs set by Eskom and Bloem Water. | Conduct a cost of supply study reflective and introduce cost reflective tariffs considering affordability of consumers. | In-house | In-house | CM and CFO | 01/08/2023 | 31/12/2023 | Cost-reflective tariffs Cost-of-Supply Studies Trading Services Surpluses | Cost-of-Supply Reports Tariff Structures | Inrease in Revenue, based on the revised tariffs
Perform cost-volume profit analysis before setting the base tariff for water electricity.
Forecast tariffs that align with the rate of growth of tariffs forecasted by Bloem Water.
Negotiations should be held with Bloem Water as regards their bulk tariffs.
Forecast tariffs that align with the rate of growth of tariffs forecasted by ESKOM.
6 | Indigent Management | The indigent policy was reviewed during June 2022 however not yet approved and adopted. It has 52 925 active accounts and 1 261 inactive accounts. The indigent register is not updated and reviewed on a regular basis, that can lead to cash leakage and misalignment with the equitable share allocation. Revenue billing and collection targets will not be reached as customers may inappropriately receive free basic services. Revenue Loss. Indigent register not credible. | Adopt and implement the approved Indigent Household Policy and by-laws. | In-house | In-house | MM, CFO, Director: Corporate Services | 01/08/2023 | 31/12/2023 | Updated Indigent Management Policy Complete Indigent Register Adjusted Debtors Book | Indigent Management Policy Updated Indigent Register | Reduction in expenditure from curbing the supply of services to non-indigents
A quantitative Cost Benefit Analysis should be carried out to determine the most financially optimal option for the verification of indigent household. This is essentially an evaluation of manual verification compared to obtaining a system.
Updating and cleansing of data on the system to provide correct details of customers.
Information captured on the system is reviewed by senior personnel for accuracy and completeness.
Errors on the system are immediately corrected as they are identified.
7 | Supply Chain Management Compliance and Value for Money Procurement | Unspent conditional grants as at 30 June 2022 total R571.0 million. There is insufficient cash on hand to cover payables and unspent conditional grants hence underspending on the capital budget. This is an indication that conditional grants have been spent on operating expenditure. Insufficient financial and project management. As at 30 June 2022 MMM has already committed R 258 million on capital projects which they have not yet provided funding for. High unauthorised, irregular and fruitless and wasteful expenditure (UIF&W) is disclosed in the financial statements. As at 30 June 2022 the situation is as follows: Unauthorised: R 5.6 billion. Irregular: R 3.1 billion. Fruitless and Wasteful: R 240 million. There was an increase in UIF&W of R 1,7 billion (24%) from the 2020/21 to the 2021/22 financial year. Capital projects and operating services provided by contractors are not monitored. SCM Policy not adhered to. Disregard for SCM policy and regulations. | UIF&W expenditure to be interrogated with reasons therefore and to be submitted to Council for their decision on what action should be taken based on management’s recommendations. Institute legal action and consequence management based on the outcomes of the investigations. | In-house | In-house | CM and CFO | 01/08/2023 | 31/12/2023 | SCM Policy SOPs UIF&W Investigation Consequence Management Disciplinary Board PMU Office | SCM Policy SOPs approved and implemented Functioning Disciplinary Board Functioning PMU Office | Reduction in UIF&W based on FRP targets
Consequence management policy to be incorporated in HR.
Standard operating procedures need to be set for SCM.
Adhere to SCM Policy and Regulations.
The disciplinary board must become operational so that action can be taken against staff involved in criminal and legal non-compliant activities.
Compilation of the contract register and contract management policies.
Implement contract monitoring controls and adhere to this on a monthly basis.
MMM should establish a Project Management Office to ensure that contract management and value for money monitoring are affected.
Provincial or National Treasury to provide regular SCM regulations training to the SCM staff.
8 | Cost Containment and Realistic Cash Flow Management | The cash/ cost coverage ratio for 2021/22 was 0.31 months (2020/21: 0.36 months) when the norm is 1 to 3 months. The Municipality is not able to pay its short-term obligations as they fall due. Poor debtors’ collection rate which is the reason for the poor payment rate of MMM creditors. Lack of accountability and clear roles and responsibilities. Excessive expenditure with no system of control. Cost containment targets not included in performance contracts. Tariffs are not cost reflective. | Revise the Cost containment Policy in line with NT Municipal Cost Containment Regulations (2019). | In-house | In-house | CFO, NT Oversight | 01/08/2023 | 31/01/2024 | Revised Cost containment Policy Cashflow Committee Adoption of a Cash Management System Inclusion of Cost Containment in Performance Agreements Development of a System of Expenditure Control | Revised Cost containment Policy Cashflow Committee Adoption of a Cash Management System Inclusion of Cost Containment in Performance Agreements Development of a System of Expenditure Control | Cash Coverage: 1.5 Month Improved Revenue Reduction in Expenditure
Implement the approved Cost Containment Policy.
Establish a cashflow committee.
Adopt an active cash management system to enable the municipality to maintain sound liquidity.
Include cost containment targets in performance contracts.
Establish a system of expenditure control where no expenditure/ order is authorised unless it is provided for in the cash backed budget.
9 | Creditor Management | A review of the amounts owed by the Municipality reflected the following: Creditors as at 30 June 2022 is R 2,4 billion. Creditors have increased by R 216.3 million year on year, between June 2021 and June 2022. 29% of the amounts owed by MLM relates to bulk water purchases with Bloem Water. Not performing creditors reconciliations. The entity defaulted on the payment of suppliers within 30 days. The average term of payment of trade creditors during 2021/22 were 115 days, (2021: 131 days). | Pay new creditors within 30 days and design a tool for monitoring of the payment and obtain CFO and CM sign off of the tool. | In-house | In-house | CFO, Technical Director | 01/08/2023 | 31/01/2023 | MFMA 30-day Payment Compliance Renegotiated Payment Terms Data Cleansing Bloem Water Bulk Supply Tariff Review Creditor Reconciliation | MFMA 30-day Payment Compliance Renegotiated Payment Terms Data Cleansing Bloem Water Bulk Supply Tariff Review Creditor Reconciliation | 100% adherence to payment arrangements Achieve expenditure financial targets per BFP parameters
Renegotiating parts of amounts owed such as penalties relating to Eskom.
Data cleansing should also be implemented for creditor information.
Creditor reconciliations should be performed weekly and reconciling item resolved promptly.
Review the SLA with Bloem Water and re-negotiate the bulk supply tariffs.
10 | Financial Control Environment | The 2021/22 financial statements submitted were not prepared in all material respects in accordance with the requirements of Section 122(1) of the MFMA. There were material uncorrected misstatements. Qualified audit opinion. There were also material restated figures in the 2019/20 and 2020/21 AFS. High reliance on consultants for assistance in the preparation of the AFS. mSCOA strings are only 85 percent compliant. | Interim AFS should be prepared and assessed to form the base of the year-end AFS preparation. | In-house | In-house | CM, CFO, Director: Corporate Services | 01/08/2023 | 31/12/2023 | Reviewed SOP's adopted Record Management Procedure Manual Complete Audit Files Reviewed Audit Action Plan mSCOA Training | Adopted SOP’s Record Management Procedure Manual Complete Audit File mSCOA Training Attendance Register | Training expense based on budget allocation
Management should ensure that there is proper record keeping, sufficient staff members assisting with the requested information by the auditors and should submit the information timeously. This will speed up the audit and it will result in reduced audit cost for the Municipality.
Review the progress of the audit action plan immediately after the issue of the audit report, provide practical action plan and track progress thereof.
Training of internal audit on the adequate review of AFS and before submission to the AG.
Review and update the mSCOA implementation strategy.
Training of finance staff regarding mSCOA.
PILLAR FOUR: SERVICE DELIVERY
1 | Strategic positions | Key managerial technical positions as identified in the approved organogram must be filled to capacity MMM to ensure service delivery. | Appointment of permanent senior management position in line with MFMA regulations to enable service delivery. | In-house | In-house | City Manager, Director Corporate Services | 01/08/2023 | 31/12/2023 | Filling of critical vacant positions | Critical vacant positions are filled | Per the BFP
2 | Technical systems | There is a lack of technical systems to support and enable departments to ensure service delivery Complaints from the community that the response time is too long to attending to all reported faults and blockages, addressing sewage spillages, and reducing sewer blockages allude to a lack of an electronic fault and maintenance system. There is no electronic Vehicle Maintenance System, current system is manual system and inadequate. IT system landscape is not defined and implemented. Enhance revenue by installing a scada system for recording and measuring Bulk meters and Zonal meters to curb revenue losses & to detect tampers remotely. Enhance revenue by installing Bulk meters and Zonal meters to curb revenue losses & to detect tampers remotely. There is no electronic Vehicle Maintenance System, current system is manual system and inadequate. There is no GIS system in place to identify the location of assets. Building Control process is manual, the circulation process is time consuming and long winded, information gets lost during circulation and there is a shortage of staff. | Conduct a system landscape analysis based on service delivery needs and integration requirements. | City Manager, CFO, GM Budget, Service Delivery Executive Managers | In-house | City Manager | 01/07/2023 | 31/12/2023 | System Landscape Analysis Report Implementation of a GIS System | System Landscape Analysis Report Implemented GIS System | Per the BFP
|  |  | Investment is needed in a GIS system to manage all MMM assets. | [7 empty] | Per the BFP
3 | Policy and planning | SPLUMA has been implemented however MMM takes too long to sign the SLA resulting in delays as the owner cannot install services The municipality is currently developing and concluding on the following plans: • Water Master plan • Sanitation Master plan • Roads and Stormwater Masterplan • Integrated Waste Management Plan (IWMP) • Water Infrastructure Maintenance plan • Sanitation Infrastructure Maintenance plan • Roads and Stormwater Infrastructure Maintenance plan The municipality does not have the following plans in place: • Water Conservation and Water Demand Management Plan (WCWDMP); • Water Services Development Plan (WSDP) • Communitity Facilities Maintenance Plan and Operation Plan. Fleet Management Strategy and Plan should be drafted and incorporated into a Fleet Management Policy. Currently Vehicle Maintenance Plan in the Fleet Management Policy is not detailed. MMM does not have separate Insurance and Fuel Management Policy. Vehicles are insured in line with the Asset Management Policy of the Municipality and the use of fuel is covered in the Fleet Management Policy. No proper policy and service charter to improve customer service. There is no asset management policy or Asset Management Plans (AMPs) in place. A condition assessment was done however current analysis on the Asset Register does not reflect the outcomes of the assessment. Asset Register updates are poor and manual. Dilapidated components at Water Treatment Plants and sewer spillage upstream from Waste Water Treatment Works is a threat to water quality. Dilapidated components at Waste Water Treatment Works result in sewer spillage which is threat to water quality. Up to 90% of surfaced roads are in poor condition (reported potholes, stormwater drainage and related blocked drains). Lack of funding for maintenance, refurbishment and capital projects has accelerated the decline in the condition of the infrastructure resulting in failing equipment. Loadshedding is another accelerant factor. Projects for refurbish /upgrade electrical network are delayed due to insufficient budgets. Parks has a maintenance strategy in place which stipulates the maintenance standards on how Parks have to be maintained and looked after however there are not enough vehicles are available due to breakdowns and there is no maintenance budget available. Complaints from the community that the response time is too long to attending to all reported faults and blockages, addressing sewage spillages, and Reducing sewer blockages. Water Loss Management. Water losses attributed to meter tampering and illegal connections due to customers not prioritising the payment of services. Water Loss Management. Water losses are reported at 46% largely due to lack of proper network maintenance. Metering policy. | MMM to adhere to timeframes recommended by SPLUMA and capacitate the department. | In-house | In-house | City Manager | 01/08/2023 | 31/12/2023 | Adherance to SPLUMA guideline for timeframes | SLA's signed within the SPLUMA timeframes | GRAP Compliant Asset Register
|  |  | Allocate budget, complete and implement | City Manager, CFO, GM Budget, Service Delivery Executive Managers | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Masterplans for: Water Sanitation Roads and Stormwater Integrated Waste Management Plan Maintenance Plans for: Water Sanitation Roads and Stormwater | Masterplans for: Water Sanitation Roads and Stormwater Integrated Waste Management Plan Maintenance Plans for: Water Sanitation Roads and Stormwater
|  |  | Review and adopt the Fleet Management Policy and incorporate Fleet Management Strategy/Plan and Vehicle Maintenance Plan. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Adoption of the Fleet Management Policy incorporating the Strategy/Pland and Maintenance Plan | Fleet Management Policy incorporating the Strategy/Pland and Maintenance Plan
|  |  | MMM must develop separate policies for Insurance and Fuel Management separate from the Fleet Management Policy. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Adoption of the Vehicle Insurance Policy and Fuel Management Policy | Vehicle Insurance Policy and Fuel Management Policy
|  |  | Develop customer services policy and service charter. Provide adequate funding to resource customer services processes. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Adoption of the Customer Service Policy and Service Charter | Customer Service Policy and Service Charter
|  |  | Condition assessment outcomes must reflect on the asset register of MMM. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/08/2023 | 31/12/2023 | Asset Register updated with Condition assessment outcomes | Asset Register updated with Condition assessment outcomes
|  |  | Undertake an asset completeness exercise. | External | External | City Manager, Director Corporate Services, Technical Directors, CFO | 01/08/2023 | 31/12/2023 | All MMM assets are accounted for | New assets verification information Unbundled asset supporting verification and working papers
|  |  | Compile a GRAP compliant asset register. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/08/2023 | 31/12/2023 | Updated Asset Register | Updated Asset Register
|  |  | Assess useful lives and residual values of assets. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/08/2023 | 31/12/2023 | Updated Asset Register | Updated Asset Register
|  |  | Ensure that updates happen timeously with the supporting information and in compliance with GRAP and mSCOA requirements. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/08/2023 | 31/12/2023 | Updated Asset Register | Updated Asset Register
|  |  | Projects must be identified, assessed, costed and priortised on a yearly basis. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/08/2023 | 31/12/2023 | Planning and budget documentation | Planning and budget documentation
|  |  | Maintenance budgets must be allocated to Community Services to ensure the upkeep of assets. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Budget Documentation | Budget Documentation
|  |  | Maintenance budgets must be allocated to Service Delivery departments to ensure tools, spares and machinery is available to undertake repair and maintence activities. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Budget Documentation | Budget Documentation
|  |  | Approve revenue recovery strategies. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/08/2023 | 31/12/2023 | Adoption of revenue recovery strategies | Revenue recovery strategy document
|  |  | Identify pipe replacements for pipe networks contributing to water losses. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Reduced Non- Revenue Water losses | Reduced Non- Revenue Water losses
|  |  | Amend and approve metering policy to reflect the use of smart metering technologies. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Approved amened Metering Policy | Amended Metering Policy
4 | Tariffs | Bloemwater debt is R507m and the Bloemwater monthly invoices are unaffordable. | Review Bloemwater SLA. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Revised SLA with Bloemwater | Revised Bloemwater SLA | Revised tariffs based on SLA negotiations
|  |  | Review of Tariff Policy. | In-house | In-house | City Manager, Technical Director, CFO |  |  | Adoption of revised Tariff Policy | Revised Tariff Policy
|  |  | Approve revenue enhancement measures. | In-house | In-house | City Manager, Technical Director, CFO |  |  | Adoption of revenue enhancement measures | Revenue enhancement policy
5 | Metering | Water Loss Management. Water losses are reported at 46% largely due to lack of proper network maintenance. Water Loss Management. Unmetered self consumption. Need for meter audits and 'SMART' technologies due to inaccurate meter database and poor revenue collected. Faulty meters, inaccurate billing and old meters leads to incorrect billing information and estimated billing which in turn results in inaccurate billing and inflated debt. Theft, illegal connections and Meter tampering result in Electricity losses of 10.92% (Technical and non-technical losses). Malfunctioning of bulk meters due to aging and tampering. Enhance revenue by installing Bulk meters and Zonal meters to curb revenue losses & to detect tampers remotely. Government debt is about R800m due to Government departments are not honouring their debt in full. Currently 4620 meters are not allocated to the financial system and information on installed meters do not always reach the finance office. | Targeted meter replacement priortised by largest loss impact on a yearly basis. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Prioritised list of target areas | Performance against list Revenue change per area | Per the BFP
|  |  | Prioritise budget for smart meter replacements. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Prioritised list of targeted meter replacements | Performance against list
|  |  | Check meters to be installed in a phased approach. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Prioritised list of check meters to be installed | Performance against list
|  |  | Install bulk smart meters for LPU customers. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Prioritised list of LPU smart meters | Performance against list
|  |  | All municipal properties should have meters installed and the readings should be taken monthly. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | List of Municipal properties with no meters | Performance against list with supporting meter installation certificate
|  |  | Joint MMM teams (finance and engineering) should conduct in-loco inspections (audits) of metered customers. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Target 15% of metered customers per year for inspection | Inspection sheets and evidence of corrective actions (if any)
|  |  | Departments in arrears with their accounts should be treated the same as customers in arrears. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Department accounts should not exceed 60 days | Credit analysis
|  |  | Install bulk smart meters for LPU customers. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Prioritised list of LPU smart meters | Performance against list
6 | Landfill | Landfills are currently not complying to the legislation which could lead to licences been revoked. All existing landfill sites weighbridges are currently not functioning. The fences have also been stolen. There is currently no revenue collected at the landfill sites, gates except revenue from the destruction of condemned goods which is not frequent. There are no sufficient resources to cover areas that are badly affected by the illegal dumping. Furthermore, lack of sufficient human capacity to provide education and awareness to the community members. | Identify the non compliance criteria and create projects and project implementation plans to ensure compliance | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Landfill project list and accompaning project implementation plans | Landfill project list and accompaning project implementation plans | Revenue collection from weighbridges at landfill sites
|  |  | Install Weighbridges on landfill sites. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Weighbridges installed and comissioned | Project Completion Certification
|  |  | Collect revenue from users at landfill sites. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Increased revenue | Debtor statements
|  |  | Collaborate with Private waste removal companies. | In-house | In-house | City Manager, Technical Director, CFO | 01/08/2023 | 31/12/2023 | Waste collection schedules are met | Waste collection schedules are met
7 | Water quality | Compliance to Water quality standards for Blue Drop monitoring on the IRIS system. Compliance to Water quality standards for Green Drop monitoring on the IRIS system. | Implement the recommendations of the Blue Drop Report. | In-house | In-house | City Manager, Technical Director, CFO | 01/07/2023 | 31/12/2023 | Blue drop report recommendation are implemented | Evidence supporting the implementation of the recommendations | Increase in quality of water supply
|  |  | Implement the recommendations of the Green Drop Report. | In-house | In-house | City Manager, Technical Director, CFO | 01/07/2023 | 31/12/2023 | Green drop report recommendation are implemented | Evidence supporting the implementation of the recommendations
8 | Asset security | Service delivery infrastructure is vandalised. All existing landfill sites weighbridges are currently not functioning. The fences have also been stolen. There is currently no revenue collected at the landfill sites, gates except revenue from the destruction of condemned goods which is not frequent. | Review Security Contracts entered into to secure key facilities. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/07/2023 | 31/12/2023 | Security contract should be a combination of least cost and value for money | Reviewed security contracts | Reduction in repairs and maintenance due to decreased vandalism
|  |  | Use technology to augment the security personnel such as alarm systems and camera monitoring systems with armed response. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/07/2023 | 31/12/2023 | Implementation of electrconis security measures | Implementation of electrconis security measures
|  |  | Use of the same above-mentioned security to safeguard smaller infrastructure sites prone to vandalism but not large enough to warrant a permament warm body. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/07/2023 | 31/12/2023 | Implementation of electrconis security measures | Implementation of electrconis security measures
9 | Project Management | Time taken to reticulate peri-urban areas is too long leading to community protests. The rate of rehabilitation and development of sewer reticulation networks is very slow. Lack of funding for maintenance, refurbishment and capital projects has accelerated the decline in the condition of the infrastructure resulting in failing equipment. Loadshedding is another accelerant factor. Projects for refurbish /upgrade electrical network are delayed due to insufficient budgets. | Introduce a monitoring mechanism to track project progress against spend, be a repository for project capitalisation purposes to assist in the capitalisation process. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/07/2023 | 31/12/2023 | Implement a project tracking system | Project tracking system | 100% Capital Expenditure
|  |  | Review expenditure on Capital projects to ensure the funds received are spent in accordance with the given conditions. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/07/2023 | 31/12/2023 | No grant spending withdrawn due to not meeting the conditions of the Grant/s | Grant reporting frameworks
|  |  | An integrated approach is needed for multidiciplinary projects. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/07/2023 | 31/12/2023 | All project must have a Project Implementation Plan | Project Implementation Plan
|  |  | Project prioritsation matrix must be developed. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/07/2023 | 31/12/2023 | Implementation of a project prioritisation matrix | Project prioritisation matrix
|  |  | All projects must feed into the CAPEX plan and have an associated Project Implementation plan. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/07/2023 | 31/12/2023 | All project must have a Project Implementation Plan | Project Implementation Plan
|  |  | Ring fence of grant funds and preferably pay service providers from this dedicated account in order to monitor and minimise misuse. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/07/2023 | 31/12/2023 | Timeous payment of service providers used on grant funded projects | Payment remittance
10 | Plant and Fleet | Inadequate plant and equipment to manage the landfill sites. There is a refuse removal schedule, but it is frequently not adhered to due to lack of sufficient vehicles to remove waste and lack sufficient human resources (critical positions not filled). The mechanical workshop is in a good condition but under utilized due to budget constraints to procure adequate and specialized equipment and spares. Dysfunctional plant, equipment and fleet that cannot be repaired or salvaged should be disposed off. Parks has a maintenance strategy in place which stipulates the maintenance standards on how Parks have to be maintained and looked after however there are not enough vehicles are available due to breakdowns and there is no maintenance budget available. | A comprehensive needs analysis including cost benefit analysis on the maintenance costs and lease vs buy analysis should be implemented in the Fleet strategy. | In-house | In-house | City Manager, Technical Director, CFO | 01/07/2023 | 31/12/2023 | Fleet Management strategy | Fleet Management Strategy Cost benefit analysis on maintenance costs | Per vehicle replacement plan
|  |  | Review the current existing lease agreements and perform a cost benefit analysis on leasing versus buying. | In-house | In-house | City Manager, Technical Director, CFO | 01/07/2023 | 31/12/2023 | Reviewed lease agreements | Lease vs buy analysis
|  |  | Incorporate the vehicle replacement plan under Fleet management strategy plan. | In-house | In-house | City Manager, Technical Director, CFO | 01/07/2023 | 31/12/2023 | Fleet Management strategy | Vehicle replacement plan
|  |  | Budget for the mechancial workshop must be provided for. | In-house | In-house | City Manager, Technical Director, CFO | 01/07/2023 | 31/12/2023 | Budget Documentation | Budget Documentation
11 | Training | Need for meter audits and 'SMART' technologies due to inaccurate meter database and poor revenue collected. | Meter readers should have technical skills and should report on illegal connections or meter tampering. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/07/2023 | 31/12/2023 | Meter reading exception reporting on tampering and illegal connections | Meter reading exception reporting on tampering and illegal connections | Per approved training budget allocation
|  |  | Provide training in grant conditions and guidelines. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/07/2023 | 31/12/2023 | Training of Project Managers on grant conditions and guidelines | Training attendance and certification
12 | Housing delivery | There is an influx of people to Mangaung resulting in an increase in population and informal settlements which adds to the backlogs. | Allocate budget for the eradicate the VIP toilets in a phase approach. | In-house | In-house | City Manager, Technical Director, CFO | 01/07/2023 | 31/12/2023 | Budget Documentation | Budget Documentation | Per the BFP
Note on K170: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please correct the terminology if I got it wrong

## STABILISATION PHASE 2
PHASE 2: STABILISATION
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR ONE: GOVERNANCE
1 | Governance, Council and oversight structures/Committees | The municipality does not have a stakeholder engagement strategy and public participation policy in place. Disciplinary Board not in place and therefore not functional. | Develop and implement a stakeholder engagement strategy that introduces various stakeholder engagement forums such as bi-weekly MLM team chats with the Accounting Officer. | In house | In house | CM, Director: Corporate Support Services | 01.01.2024 | 31.01.2024 | By-in and informed stakeholders | Approved stakeholder engagment strategy an implemetation plan. | Financial benefits to be achieved through improved operational efficiencies
|  |  | Implement a register for open cases and status. | In house | In house | CFO | 01/01/2024 | Monthly | Financial misconduct recorded. | Financial misconduct register
|  |  | Disciplinary Board to report on investigation of all reported allegations of financial misconduct. | In house | In house | Disciplinary Board | 01/01/2024 | Quarterly | Quarterly reports | Council approved reports and resolutions
2 | System of Delegations | Non-compliance with legislation specifically Municipal Systems Act that requires review of system of delegations after every local government election. | Review and approve delegations of powers and functions for implementation of supply chain management policy. | In house | In house | CM and CFO | 01/01/2024 | 30.07.2024 | Enhanced accountability and, checks and balances. Sub-delegations in place | Approved SCM Delegations of authority | Financial benefits to be achieved through improved operational efficiencies
3 | UIF&W and Consequence Management | There are no section 32 investigations that have been conducted. The analysis and identification of UIF&W was outsourced but the report is not being used by the municipality due to the irregular appointment of the service provider. | Implement Consequence Management for historical Irregular expenditure and take steps to recover or rectify such expenditure and to prevent recurrence as prescribed by section 32 of the MFMA. | In house | In house | CM | 01/01/2024 | 31/12/2024 | Transgressors disciplined | Written outcome of disciplinary hearings | Financial benefits to be achieved through improved operational efficiencies
4 | Audit action plans (internal and external) | AFS/APR may contain misstatement due to employee’s lack of knowledge or understanding of the current standards and regulations. | Provide budget for training. | In house | In house | CM | 01/01/2024 | 31/12/2024 | Report tabled to Audit Committee, Mayoral Committee and Council | Agenda and minutes of Mayoral committee and Council, and recommendations and resolutions | Financial benefits to be achieved through improved operational efficiencies
5 | Risk Management | Inadequate diagnosis of all relevant risks being faced by MMM | Ensure that risk management is a standing agenda item for all scheduled management and Executive meetings. | In house | In house | CM CRO | 01/01/2024 | 31/12/2024 | Monitored risks | Quarterly risk management reports approved by Administrator. Risk monitoring report. Monthly FRP implementation progress reports | Financial benefits to be achieved through improved operational efficiencies
6 | Information and Communication Technology | Internal Control Deficiencies. | Review, develop and implement ICT general controls (policies and SOPs). | In house | In house | ICT Manager | 01/01/2024 | 31/12/2024 | Improved intenal controls | Approved ICT policies and SOPs | Financial benefits to be achieved through improved operational efficiencies
PILLAR TWO: INSTITUTIONAL
1 | Operating Model | MMM does not have a well-defined and approved organisational structure to support the functioning of the Municipality. | The adoption and periodic review of the organisational structure in line with MMM’s approved operating model, strategy and governance structures. | In-house | In-house | CM, Director : Corporate Services | 01/01/2024 | 31/12/2024 | Credible staff establishment in line with the reviewed operating model. | Placement letters Copies of the job descriptions | In line with the approved budget and the funding plan.
|  | Inadequate day-to-day establishment management | Continued regular staff verification and implement the recommendations of the staff verification report.
2 | Employee costs | Employee costs are currently 24.71% of the operating expenditure which is below the norm of 25%-40%. The low % could point to a high level of critical vacancies and general understaffing. | Control over payroll by planning for the acquisition of skills in line with cash flow improvements. | In-house | In-house | CFO, Director : Corporate Services | 01/01/2024 | 31/12/2024 | Controlled employee costs | Skills Acquisition plan | Per BFP
3 | Management of overtime | Excessive Overtime. | Conduct quarterly monitoring of the implementation of the Overtime Policy by department. | In house | In house | D: CSS | 01/01/2024 | Quarterly | Reduced Overtime costs | Quarterly overtime monitoring reports | Reduction in Employee cost
4 | Filling of critical positions | Limited capacity and skills to facilitate compliance with the Municipal Minimum Competency Framework. | Review Recruitment policy and procedures to ensure checks and balances that mitigate irregular practices. | In house | In house | CM, CFO and Director Corporate Services | 01/01/2024 | 31/12/2024 | Approved reviewed Recruitment policy | Approved reviewed Recruitment policy | Per approved budget allocation
Ringfence mandatory grant from LGSETA and other related capacity building grants for training and development of staff.
|  |  | Appoint accredited service provider to assist with the WSP implementation. | [6 empty] | Service Provider appointment letter & SLA | Per approved budget allocation
5 | Staff discipline | Ineffective disciplinary processes. | Utilise officials from other government departments, municipalities and or SALGA database to conduct disciplinary cases on behalf of the municipality. | Outsource | Outsource | CM and D: CSS | 01/01/2024 | Ongoing | Effective discipline management. | Signed Agreementswith SALGA and other departments, consultations outcomes. | N/A
6 | Consequence Management | Lack of accountability and consequence management in the municipality impacts service delivery and municipal finance management. | Continued monitoring of the implementation of the consequence management policy. | In-house | In-house | Director Corporate Services | 01/01/2024 | Ongoing | Consequence management policy implementation | Consequence management policy implementation | N/A
7 | Key HR Policies Management | Poor Human Resource Planning and excessive overtime. | Enforcement of compliance to the Basic conditions of Employment Act for the management of overtime by managers. | In-house | In-house | Director Corporate Services S56 Managers | 01/01/2024 | Ongoing | Reduced Overtime costs | Reduced Overtime costs | Reduction in Employee cost
8 | Change Management | Change Management is not implemented. | Continued monitoring of the change management strategy. | In-house | In-house | Director Corporate Services | 01/01/2024 | Ongoing | Change Manegement Strategy | Change Manegement Strategy | N/A
PILLAR THREE: FINANCIAL MANAGEMENT
1 | ESKOM | Escalating ESKOM debt. | Consider application for MFMA Circular No. 124 – Municipal Debt Relief through National Treasury. | In-house | In-house | CM and CFO | 01/01/2024 | 12 Months | Maintaining the Eskom bulk current account A funded MTREF Cost reflective tariffs Electricity and water as collection tools 80% average quarterly collection of property rates and service charges Municipality’s billing system perfectly aligns to its Council approved GVR MFMA section 71 reporting Monthly reporting on progress in implementing its FRP to the Provincial Executive Provincial Treasury certification of Municipal compliance Limitation on Municipality borrowing powers Ensure proper management of resources | Monthly Provincial Treasury certification of Municipal compliance | Municipal Eskom Debt Relief as prescribed by Circular No. 124
|  |  | Adhere to the requirements and terms. |  |  |  | 01/01/2024 | Monthly
2 | Adjustment Budget for 2023/24 | During the 2020/21 and 2021/22 financial years, MMM budgeted surpluses of R 1,035 billion (2020/21) and R 622,7 million (2021/22). The financial results for the two years reflected deficits of R 20,2 million (2020/21) and a deficit of R 872,7 million (2021/22) which clearly indicate that the budgets were not funded. MMM had audited deficits for the past three financial years, and budget for surpluses for the MTREF period, which are not cash backed. | Compile a 2023/24 adjustment budget in line with reviewed targets for realistically anticipated revenue and expenditure trends and ensure revised budget to be credible and cash funded. | In-house | In-house | CFO | 01/01/2024 | 30/05/2024 | Credible 2024/25 MTREF Adjustment Budget Cost Containment Improvement | Credible 2024/25 MTREF Adjustment Budget Cost Containment Improvement | Proper baseline for long term financial planning.
Projected revenue should consider the low historical and future collection rates and use a probabilistic method of projecting for revenue.
Austerity and cost cutting measures to be reflected in the 2023/24 adjustment budget.
3 | Supply Chain Management Compliance and Value for Money Procurement | Retention of supporting documentation not complete. Lack of record keeping. Lack of consequence management regarding irregular expenditure incurred. | Consequence management policy to be incorporated in HR. | In-house | In-house | CFO, Director Corporate Services | 01/01/2024 | 31/12/2024 | Consequence Management Policy Attendance Register on Training Record Keeping System | Consequence Management Policy Attendance Register on Training Record Keeping System | Reduction in UIF&W based on FRP targets
Training of staff regarding the SCM processes.
Implementation of a record keeping system.
4 | ENTITY: CENTLEC | The principal activity of CENTLEC is the distribution of electricity to industries, businesses and households mainly in the Mangaung and Southern Free State areas. The relevant balances as at 30 June 2022 are: • Cash on hand R509.3 million; • Payables R890.8 million; • Deficit R189,5 million 2022 and R13.7 million 2021; • Employee related costs R425.6 million; • Duplication of management and board members; and • MMM not able to use electricity as a lever for collection of other debts e.g., rates, water, etc. From the above figures it is noted that Centlec has serious going concern challenges, operating on deficits and does not have sufficient cash at hand to settle short term liabilities. | Review the assessment conducted by EMS Solutions (Pty) Ltd on the consideration for the viability and implications of the sale of Centlec and incorporation of the Entity into MMM. | CM and CFO | NT Oversight | CM | 01/01/2024 | 31/12/2024 | Reviewed assessment report of EMS Solutions (Pty) S78 Assessment Report | Reviewed assessment report of EMS Solutions (Pty) S78 Assessment Report | Possible increase in revenue based on the outcome of the S78 investigation
Conduct a Section 78 study to see the possibility of incorporating CENTLEC into MMM. As it currently stands, and before re-incorporating this service into the Municipality, CENTLEC’s performance must be monitored continuously.
5 | ENTITY: FRESHCO | Per the consultation process, it was established that the non-payment of water and rental accounts followed the liquidation of the managing company, FRESHCO, and the takeover of administration by the Social Housing Regulatory Authority (SHRA) in 2019. As per the group AFS as at 30 June 2022, FRESCO had liabilities of R149.5 million. Poor financial performance and growing liabilities. | Conduct a Section 78 study to see the possibility of incorporating FRESHCO into MMM. As it currently stands, and before re-incorporating this service into the Municipality, FRESHCO’s performance must be monitored continuously. | CM and CFO | NT Oversight | CM | 01/01/2024 | 31/12/2024 | S78 Assessment Report | S78 Assessment Report | Possible increase in revenue based on the outcome of the S78 investigation
6 | Creditor Management | A review of the amounts owed by the Municipality reflected the following: Creditors as at 30 June 2022 is R 2,4 billion. Creditors have increased by R 216.3 million year on year, between June 2021 and June 2022. The entity defaulted on the payment of suppliers within 30 days. The average term of payment of trade creditors during 2021/22 were 115 days, (2021: 131 days). | Provide budgetary allocation in budget to meet the payment plans for long outstanding creditors. | In-house | In-house | CFO, Technical Director | 01/01/2024 | 31/12/2024 | Renegotiated Payment Terms Consequence Management | Renegotiated Payment Terms Consequence Management | 100% adherence to payment arrangements Achieve expenditure financial targets per BFP parameters
Implement consequence management.
PILLAR FOUR: SERVICE DELIVERY
1 | Technical systems | There is a lack of technical systems to support and enable departments to ensure service delivery Complaints from the community that the response time is too long to attending to all reported faults and blockages, addressing sewage spillages, and reducing sewer blockages allude to a lack of an electronic fault and maintenance system. There is no electronic Vehicle Maintenance System, current system is manual system and inadequate. IT system landscape is not defined and implemented. Enhance revenue by installing a scada system for recording and measuring Bulk meters and Zonal meters to curb revenue losses & to detect tampers remotely. Enhance revenue by installing Bulk meters and Zonal meters to curb revenue losses & to detect tampers remotely. There is no electronic Vehicle Maintenance System, current system is manual system and inadequate. There is no GIS system in place to identify the location of assets. Building Control process is manual, the circulation process is time consuming and long winded, information gets lost during circulation and there is a shortage of staff. | Based on the system landscape outcomes, invest in an electronic fault and maintenance system. | In-house and External service provider | In-house | City Manager | 01/01/2024 | 31/12/2024 | Implementation of an Electronic fault and maintentance system Implementation of an electronic Vehicle Maintance system Implementation plan to implement the recommendations Allocation of budgets Implementation of a Scada system Implementation of a Vehicle Maintence system Implementation of a Building Control system Training of software champions on all software implemented | Implemented Electronic fault and maintenance system Implemented electronic Vehicle Maintanance system Implementation plan Budget documentation Implemented Scada System Implemented Vehicle Mantenance system Implemented Building control system Training attendance and certification | Per the BFP
|  |  | Based on the system landscape outcomes, invest in an electronic Vehicle Maintenance system. | In-house and External service provider | In-house | City Manager | 01/01/2024 | 31/12/2024
|  |  | Allocate budget to implement the recommendations of the outcomes of the systems landscape analysis. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2024 | 31/12/2024
|  |  | Investment in a Scada system is needed. | In-house and External service provider | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2024 | 31/12/2024
|  |  | Based on the system landscape outcomes, invest in an electronic Vehicle Maintenance system. | In-house and External service provider | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2024 | 31/12/2024
|  |  | Based on the system landscape outcomes, invest in an electronic Building Control system. | In-house and External service provider | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2024 | 31/12/2024
|  |  | Software champions must be identified and fully trained in the software implemented. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2024 | 31/12/2024
2 | Policy and planning | SPLUMA has been implemented however MMM takes too long to sign the SLA resulting in delays as the owner cannot install services The municipality is currently developing and concluding on the following plans: • Water Master plan • Sanitation Master plan • Roads and Stormwater Masterplan • Integrated Waste Management Plan (IWMP) • Water Infrastructure Maintenance plan • Sanitation Infrastructure Maintenance plan • Roads and Stormwater Infrastructure Maintenance plan The municipality does not have the following plans in place: • Water Conservation and Water Demand Management Plan (WCWDMP); • Water Services Development Plan (WSDP) • Communitity Facilities Maintenance Plan and Operation Plan. Fleet Management Strategy and Plan should be drafted and incorporated into a Fleet Management Policy. Currently Vehicle Maintenance Plan in the Fleet Management Policy is not detailed. MMM does not have separate Insurance and Fuel Management Policy. Vehicles are insured in line with the Asset Management Policy of the Municipality and the use of fuel is covered in the Fleet Management Policy. No proper policy and service charter to improve customer service. There is no asset management policy or Asset Management Plans (AMPs) in place. A condition assessment was done however current analysis on the Asset Register does not reflect the outcomes of the assessment. Asset Register updates are poor and manual. Dilapidated components at Water Treatment Plants and sewer spillage upstream from Waste Water Treatment Works is a threat to water quality. Dilapidated components at Waste Water Treatment Works result in sewer spillage which is threat to water quality. Up to 90% of surfaced roads are in poor condition (reported potholes, stormwater drainage and related blocked drains). Lack of funding for maintenance, refurbishment and capital projects has accelerated the decline in the condition of the infrastructure resulting in failing equipment. Loadshedding is another accelerant factor. Projects for refurbish /upgrade electrical network are delayed due to insufficient budgets. Parks has a maintenance strategy in place which stipulates the maintenance standards on how Parks have to be maintained and looked after however there are not enough vehicles are available due to breakdowns and there is no maintenance budget available. Complaints from the community that the response time is too long to attending to all reported faults and blockages, addressing sewage spillages, and Reducing sewer blockages. Water Loss Management. Water losses attributed to meter tampering and illegal connections due to customers not prioritising the payment of services. Water Loss Management. Water losses are reported at 46% largely due to lack of proper network maintenance. Metering policy. | Develop and implement the following: 1) Water Conservation and Water Demand Management Plan (WCWDMP). 2) Water Services Development Plan (WSDP). 3) Community facilities Mantenance and operational plan. | In-house/ External service provider | In-house/ External service provider | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024 | Water Conservation and Water Demand Management Plan (WCWDMP). Water Services Development Plan (WSDP). Community facilities Mantenance and operational plan. Budget Documentation Asset condition assessment reporting All propect to have a accompaning Feasibility study Projects completed in the finacial year are accounted for in the asset register MTREF budgets Increased maintenance budgets Implemented revenue recovery strategies | Water Conservation and Water Demand Management Plan (WCWDMP). Water Services Development Plan (WSDP). Community facilities Mantenance and operational plan. Budget Documentation Asset condition assessment reporting Feasibility studies for approved projects Asset accounting Project prioritsation outcomes supporting projects on the budget Budget Documentation Financial reporting on the impact of the strategies | GRAP Compliant Asset Register
|  |  | Allocate budget and implement above | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Compile a report with a condition of all infrastructure and state of each. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Improve planning and implementation. Table feasibility studies for projects. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Ensure that updates happen timeously with the supporting information and in compliance with GRAP and mSCOA requirements. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Projects must be listed on the MTREF budgets as per the priorities. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Allocate funds for refurbishment and upgrading the Electrical infrastructure assets | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Projects must be listed on the MTREF budgets as per the priorities | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Allocate funds for refurbishment and upgrading for Waste Water Treatment plants | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Identify suitable funding sources to ensure road infrastructure is properly maintained. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Allocate funds for refurbishment and upgrading of Water Treatment Plants. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Maintenance budgets must be allocated to Community Services to ensure the upkeep of assets. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Maintenance budgets must be allocated to Service Delivery departments to ensure tools, spares and machinery is available to undertake repair and maintence activities. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Implement revenue recovery strategies. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Allocate funds for refurbishment and upgrading. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
3 | Tariffs | Bloemwater debt is R507m and the Bloemwater monthly invoices are unaffordable. | Implement revenue enhancement measures. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024 | Implementation of revenue enhancement measures | Implementation plan Monthly reporting on the effectiveness of implemented measures | Revised tariffs based on SLA negotiations
4 | Metering | Water Loss Management. Water losses are reported at 46% largely due to lack of proper network maintenance. Water Loss Management. Unmetered self consumption. Need for meter audits and 'SMART' technologies due to inaccurate meter database and poor revenue collected. Faulty meters, inaccurate billing and old meters leads to incorrect billing information and estimated billing which in turn results in inaccurate billing and inflated debt. Theft, illegal connections and Meter tampering result in Electricity losses of 10.92% (Technical and non-technical losses). Malfunctioning of bulk meters due to aging and tampering. Enhance revenue by installing Bulk meters and Zonal meters to curb revenue losses & to detect tampers remotely. Government debt is about R800m due to Government departments are not honouring their debt in full. Currently 4620 meters are not allocated to the financial system and information on installed meters do not always reach the finance office. | Targeted meter replacement priortised by largest loss impact on a yearly basis. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024 | Prioritised list of targeted areas to be updated bi-annually Secure budgets for Meter replacements Secure budgets for Zonal meter installations Loss calcuations must take into account own use Target 15% year on year for metered in-loco inspections Removal of illegal connections Established revenue loss recognition strategies | Prioritised list of targeted areas to be updated bi-annually Secure budgets for Meter replacements Secure budgets for Zonal meter installations Loss calcuations must take into account own use Target 15% year on year for metered in-loco inspections Removal of illegal connections Established revenue loss recognition strategies | Per the BFP
|  |  | Prioritise budget for smart meter replacements. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Zonal meters to be installed in a phased approach. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | The calculation of distribution losses should correctly deduct internal usage and the Rand value should be based on the cost of purchase. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Joint MMM teams (finance and engineering) should conduct in-loco inspections (audits) of metered customers. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Enforce by-laws and disconnect illegal connections. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Determine pattern of household usage and flag for any irregularities. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Equip meter readers with technical skills so they can report on illegal connections or meter tampering. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
5 | Landfill | Landfills are currently not complying to the legislation which could lead to licences been revoked. All existing landfill sites weighbridges are currently not functioning. The fences have also been stolen. There is currently no revenue collected at the landfill sites, gates except revenue from the destruction of condemned goods which is not frequent. There are no sufficient resources to cover areas that are badly affected by the illegal dumping. Furthermore, lack of sufficient human capacity to provide education and awareness to the community members. | Allocate budget for projects to remove non compliance. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024 | Secure budgets for projects Projects listed on MTREF Project have Project Implentation Plan Project priortised as per project prioritasation matrix Implementation of Waste Management Maintenance and Refurbishment plan Internal reporting on waste removal service delivery | Budget documentation MTREF Project implementation plan Project priortisation outcomes Waste Management Maintenance and Refurbishment plan Internal reporting on waste removal service delivery | Revenue collection from weighbridges at landfill sites
|  |  | Implement projects to remove non compliance. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Design and implement Waste Management Maintenance and Refurbishment Plan. | In-house/ External service provider | In-house/ External service provider | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Internalise waste removal service. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
6 | Asset security | Service delivery infrastructure is vandalised. All existing landfill sites weighbridges are currently not functioning. The fences have also been stolen. There is currently no revenue collected at the landfill sites, gates except revenue from the destruction of condemned goods which is not frequent. | Consider collaborations with SAPS, district municipality. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2024 | 31/12/2024 | Collabration documents Community engagements Procecution counts | Collaboration documents Minutes of meetings and resolutions Tracking of resolutions Community engagement Prosecution counts and outcomes | Reduction in repairs and maintenance due to decreased vandalism
|  |  | Constant community engagements to use the communities as watchdogs of municipal infrastructure. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2024 | 31/12/2024
|  |  | Enforce prosecution of perpetrators responsible for vandalism and theft. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2024 | 31/12/2024
7 | Project Management | Time taken to reticulate peri-urban areas is too long leading to community protests. The rate of rehabilitation and development of sewer reticulation networks is very slow. Lack of funding for maintenance, refurbishment and capital projects has accelerated the decline in the condition of the infrastructure resulting in failing equipment. Loadshedding is another accelerant factor. Projects for refurbish /upgrade electrical network are delayed due to insufficient budgets. | All projects must feed into the CAPEX plan and have an associated Project Implementation plan and Feasibility study. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2024 | 31/12/2024 | Projects listed on MTREF Establishment of Local contractors database Implementation of a procument plan | MTREF Local contractor database Procurement plan | 100% Capital Expenditure
|  |  | Create a database for Local Subcontractors. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2024 | 31/12/2024
|  |  | Implementation of procurement plan. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2024 | 31/12/2024
|  |  | Capital projects should be included in the three-year rolling internal audit plan. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2024 | 31/12/2024
8 | Plant and Fleet | Inadequate plant and equipment to manage the landfill sites. There is a refuse removal schedule, but it is frequently not adhered to due to lack of sufficient vehicles to remove waste and lack sufficient human resources (critical positions not filled). The mechanical workshop is in a good condition but under utilized due to budget constraints to procure adequate and specialized equipment and spares. Dysfunctional plant, equipment and fleet that cannot be repaired or salvaged should be disposed off. Parks has a maintenance strategy in place which stipulates the maintenance standards on how Parks have to be maintained and looked after however there are not enough vehicles are available due to breakdowns and there is no maintenance budget available. | Optimise the current fleet to provide maximum services. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024 | Fleet Management reporting Reporting from the fleet management system is acted timeously on Accident committee Budget documentation | Fleet management system reporting Fleet management system reporting Committee minutes and resolutions Budget documentation | Per vehicle replacement plan
|  |  | Fleet records should be updated on time and accident committee should be established to monitor progress of all fleet damaged. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Establish accident committee that will investigate all accidents and apply consequence management where necessary. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
|  |  | Budget for the mechancial workshop must be provided for. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024
9 | Housing delivery | There is an influx of people to Mangaung resulting in an increase in population and informal settlements which adds to the backlogs. | Accelerate the implementation of new human settlements developments following an integrated approach across all departments aligned to the Project Management Focus area key activities. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2024 | 31/12/2024 | Project Implementation plan Project feasibility study Project priortised as per matrix Projects listed on MTRF | Project Implementation plan Project feasibility study Project priortised as per matrix Projects listed on MTRF | Per the BFP

## SUSTAINABILITY PHASE 3
PHASE 3: SUSTAINABILITY
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR THREE: GOVERNANCE
To be informed by progress and achievements on Phase 1 and 2
PILLAR THREE: INSTITUTIONAL
To be informed by progress and achievements on Phase 1 and 2
PILLAR THREE: FINANCIAL MANAGEMENT
1 | ESKOM | Escalating ESKOM debt. | Consider application for MFMA Circular No. 124 – Municipal Debt Relief through National Treasury. | In-house | In-house | CM and CFO | 01/07/2025 | 12 Months | Maintaining the Eskom bulk current account A funded MTREF Cost reflective tariffs Electricity and water as collection tools 80% average quarterly collection of property rates and service charges Municipality’s billing system perfectly aligns to its Council approved GVR MFMA section 71 reporting Monthly reporting on progress in implementing its FRP to the Provincial Executive Provincial Treasury certification of Municipal compliance Limitation on Municipality borrowing powers Ensure proper management of resources | Monthly Provincial Treasury certification of Municipal compliance | Municipal Eskom Debt Relief as prescribed by Circular No. 124
|  |  | Adhere to the requirements and terms. |  |  |  | 01/07/2025 | Monthly
2 | Debt Restructuring | MMM has loans with DBSA, Standard Bank and Absa Bank valued at 30 June 2022 at R668 million (2020/21 R 776 million). These loans are often serviced late due to cash flow constraints. The loans in default as at 30 June 2022 totalled R382.1 million (2020/21 R 441.5 million), which is 57% of the outstanding balance. This is a further indication of the cash flow problems being experienced by MMM. During 2020, rating agency Moody’s downgraded MMM’s credit rating from B3 to Caa1. This has a negative effect on the Municipalities overall ability to obtain external funding and unfavourable interest rates. If a new rating would be done, the possibility of a further downwards adjustment is high given the current state of affairs in the Municipality. | Review the loans for a possibility to restructure, and re-negotiate payment terms. | CFO | CFO | CFO, NT Oversight | 01/01/2024 | Ongoing | Loan Restructuring Revised Payment Terms Creditor Payment Negotiations | Loan Restructuring Revised Payment Terms Creditor Payment Negotiations | More Favourable Loan Repayment and Terms
Curtail unnecessary expenditure by putting controls in place.
Make arrangements with loan creditors to repay current and outstanding amounts.
Comply with the repayment arrangements by compiling a cash backed budget.
3 | Customer care and data accuracy | The customer care unit is dysfunctional. Critical vacancies in the Customer Care Unit are not being filled. | Fill critical vacancies and train staff in customer care techniques. | In-house | In-house | City Manager, CFO, Director Corporate Services | 01/01/2024 | Ongoing | Functioning Customer Care Unit System of Queries Resolved | Functioning Customer Care Unit System of Queries Resolved | Improved revenue collection through functioning customer care
Resuscitate the billing committee, town planning and key technical personnel to form part.
Meter readers should capture changes on the properties to update the user profile.
Commission the CRM module.
Use debt collectors when appointed to update the data for the customers.
PILLAR FOUR: SERVICE DELIVERY
1 | Policy and planning | SPLUMA has been implemented however MMM takes too long to sign the SLA resulting in delays as the owner cannot install services The municipality is currently developing and concluding on the following plans: • Water Master plan • Sanitation Master plan • Roads and Stormwater Masterplan • Integrated Waste Management Plan (IWMP) • Water Infrastructure Maintenance plan • Sanitation Infrastructure Maintenance plan • Roads and Stormwater Infrastructure Maintenance plan The municipality does not have the following plans in place: • Water Conservation and Water Demand Management Plan (WCWDMP); • Water Services Development Plan (WSDP) • Communitity Facilities Maintenance Plan and Operation Plan. Fleet Management Strategy and Plan should be drafted and incorporated into a Fleet Management Policy. Currently Vehicle Maintenance Plan in the Fleet Management Policy is not detailed. MMM does not have separate Insurance and Fuel Management Policy. Vehicles are insured in line with the Asset Management Policy of the Municipality and the use of fuel is covered in the Fleet Management Policy. No proper policy and service charter to improve customer service. There is no asset management policy or Asset Management Plans (AMPs) in place. A condition assessment was done however current analysis on the Asset Register does not reflect the outcomes of the assessment. Asset Register updates are poor and manual. Dilapidated components at Water Treatment Plants and sewer spillage upstream from Waste Water Treatment Works is a threat to water quality. Dilapidated components at Waste Water Treatment Works result in sewer spillage which is threat to water quality. Up to 90% of surfaced roads are in poor condition (reported potholes, stormwater drainage and related blocked drains). Lack of funding for maintenance, refurbishment and capital projects has accelerated the decline in the condition of the infrastructure resulting in failing equipment. Loadshedding is another accelerant factor. Projects for refurbish /upgrade electrical network are delayed due to insufficient budgets. Parks has a maintenance strategy in place which stipulates the maintenance standards on how Parks have to be maintained and looked after however there are not enough vehicles are available due to breakdowns and there is no maintenance budget available. Complaints from the community that the response time is too long to attending to all reported faults and blockages, addressing sewage spillages, and Reducing sewer blockages. Water Loss Management. Water losses attributed to meter tampering and illegal connections due to customers not prioritising the payment of services. Water Loss Management. Water losses are reported at 46% largely due to lack of proper network maintenance. Metering policy. | The Electrical Masterplan is in place but should be updated at least every 5 years with the Electrical Maintenance and Refurbishment plan. | In-house and External service provider | In-house | City Manager, Technical Director, CFO | 01/01/2025 | Ongoing | Masterplan for Electrcity Maintenance Plan for Electricity Increased maintenance budgets Projects completed in the financial year are accounted for in the asset register | Masterplan for Electrcity Maintenance Plan for Electricity Budget documentation Asset accounting | Per the BFP
|  |  | Maintenance budgets must be allocated to Community Services to ensure the upkeep of assets | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2025 | Ongoing
|  |  | Ensure that updates happen timeously with the supporting information and in compliance with GRAP and mSCOA requirements. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2025 | Ongoing
|  |  | Maintenance budgets must be allocated to Service Delivery departments to ensure tools, spares and machinery is available to undertake repair and maintence activities. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2025 | Ongoing
|  |  | Accelerate the maintenance of road infrastructure. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2025 | Ongoing
|  |  | Allocate funds for refurbishment and upgrading of Infrastructure assets. | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2025 | Ongoing
2 | Tariffs | Bloemwater debt is R507m and the Bloemwater monthly invoices are unaffordable | Improve and implement revenue enhancement measures. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2025 | Ongoing | Implementation of revenue enhancement measures | Implementation plan Monthly reporting on the effectiveness of implemented measures
3 | Metering | Water Loss Management. Water losses are reported at 46% largely due to lack of proper network maintenance. Water Loss Management. Unmetered self consumption. Need for meter audits and 'SMART' technologies due to inaccurate meter database and poor revenue collected. Faulty meters, inaccurate billing and old meters leads to incorrect billing information and estimated billing which in turn results in inaccurate billing and inflated debt. Theft, illegal connections and Meter tampering result in Electricity losses of 10.92% (Technical and non-technical losses). Malfunctioning of bulk meters due to aging and tampering. Enhance revenue by installing Bulk meters and Zonal meters to curb revenue losses & to detect tampers remotely. Government debt is about R800m due to Government departments are not honouring their debt in full. Currently 4620 meters are not allocated to the financial system and information on installed meters do not always reach the finance office. | Maintain meter replacement priortised by largest loss impact on a yearly basis. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2025 | Ongoing | Prioritised list of targeted areas to be updated bi-annually Secure budgets for Meter replacements Removal of illegal connections Established revenue loss recognition strategies | Prioritised list of targeted areas to be updated bi-annually Secure budgets for Meter replacements Removal of illegal connections Established revenue loss recognition strategies
|  |  | Maintain budget for smart meter replacements. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2025 | Ongoing
|  |  | Enforce by-laws and disconnect illegal connections. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2025 | Ongoing
|  |  | Determine pattern of household usage and flag for any irregularities. | In-house | In-house | City Manager, Technical Director, CFO | 01/01/2025 | Ongoing
4 | Asset security | Service delivery infrastructure is vandalised. All existing landfill sites weighbridges are currently not functioning. The fences have also been stolen. There is currently no revenue collected at the landfill sites, gates except revenue from the destruction of condemned goods which is not frequent. | Enforce prosecution of perpetrators responsible for vandalism and theft | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2025 | Ongoing | Procecution counts | Prosecution counts and outcomes
5 | Project Management | Time taken to reticulate peri-urban areas is too long leading to community protests. The rate of rehabilitation and development of sewer reticulation networks is very slow. Lack of funding for maintenance, refurbishment and capital projects has accelerated the decline in the condition of the infrastructure resulting in failing equipment. Loadshedding is another accelerant factor. Projects for refurbish /upgrade electrical network are delayed due to insufficient budgets. | All projects must feed into the CAPEX plan and have an associated Project Implementation plan and Feasibility study | In-house | In-house | City Manager, Director Corporate Services, Technical Directors, CFO | 01/01/2025 | Ongoing | Project Implementation plan Project feasibility study Project priortised as per matrix Projects listed on MTRF | Project Implementation plan Project feasibility study Project priortised as per matrix Projects listed on MTRF